## Slide 1: Project Scope and Approach

## Slide 2: Seven Corners Travel Insurance - Customer Service Virtual Assistant

## Slide 3: Project Scope and Approach Document
Project Name: Customer Service Virtual Assistant Organization: Seven Corners Travel Insurance Document Version: 1.0 Date: 2025-10-10 Status: Draft - Awaiting Stakeholder Review

## Slide 4: Objective
To improve customer satisfaction scores by 25% and reduce average customer service response time by 50% within 12 months by implementing an AI-powered virtual assistant using Microsoft Copilot Studio and Azure AI Foundry that provides 24/7 multilingual support, automates responses to common inquiries, and seamlessly escalates complex cases to human agents for Seven Corners' diverse customer base of individual travelers, groups, expatriates, and digital nomads.
Success Metrics
Customer Experience:
Customer Satisfaction (CSAT) score increase from baseline to 25% improvement
Average response time reduction from current baseline to 50% faster
First-contact resolution rate of 60% or higher for automated interactions
Net Promoter Score (NPS) improvement of 15+ points
Operational Efficiency:
40% containment rate (inquiries resolved by virtual assistant without human escalation)
Average handle time reduction of 30% for human agents
24/7 availability with <2 second average response time
Support for minimum 5 languages (English, Spanish, French, German, Mandarin)
Business Impact:
Cost per customer interaction reduced by 35%
Call center volume reduction of 30-40% for routine inquiries
Improved agent productivity (focus on high-value interactions)
Competitive differentiation in travel insurance market

## Slide 5: Scope
Project Deliverables
Phase 1: Foundation (Months 1-3)
Copilot Studio Virtual Assistant (MVP)
  Conversational AI interface for website chat
  Top 10 most common customer inquiries automated
  FAQ knowledge base with 50+ question variations
  Human handoff capability with transcript preservation
  Multi-language support (English, Spanish as minimum)
Azure AI Search Knowledge Base
  Indexed policy documents, coverage summaries, FAQs
  Semantic search capability for natural language queries
  Integration with SharePoint or Azure Blob Storage
  Search relevance tuning and optimization
Integration Layer
  Read-only API access to policy administration system (policy lookup)
  Customer authentication for personalized responses
  Analytics dashboard for conversation monitoring
Documentation and Training
  Conversation design documentation
  Customer service team training materials
  System administration guide
  Customer communication materials
Phase 2: Expansion (Months 4-9)
Multi-Channel Deployment
  Mobile app integration
  Microsoft Teams channel (for internal/partner use)
  WhatsApp Business integration
  Facebook Messenger support
Enhanced Capabilities
  Top 30 customer inquiries automated
  Claims status tracking (read-only integration)
  Travel advisory notifications (CDC, State Department feeds)
  Proactive notifications (policy renewal reminders, claim updates)
Advanced Integration
  Policy administration system (create service requests)
  CRM integration (customer history, preferences)
  Payment gateway (policy quotes, premium payments)
Phase 3: Advanced AI (Months 10-18)
Azure AI Foundry Custom Models
  Personalized policy recommendation engine
  Intent classification model trained on Seven Corners data
  Sentiment analysis for prioritized escalation
  Predictive analytics for customer needs
Voice Channel
  Phone-based virtual assistant using Azure Voice Live API
  Speech-to-text for insurance terminology
  Integration with existing call center platform
Multi-Agent System
  Specialist agents (policies, claims, billing, travel assistance)
  Coordinated handoffs between specialist agents
  Unified customer experience across agents
In Scope
Functional Requirements:
Answer frequently asked questions about policies, coverage, claims
Look up customer policy details by policy number or customer identification
Check claim status and provide updates
Provide travel advisories and destination-specific guidance
Guide customers through policy selection based on needs
Collect customer information for service requests
Escalate to human agents when needed with full context
Support multiple languages for international travelers
Operate 24/7 with consistent quality
Technical Requirements:
Microsoft Copilot Studio for conversational interface
Azure AI Search for knowledge base and document retrieval
Azure AI Foundry for advanced AI capabilities (Phase 3)
Integration with existing systems (policy admin, CRM, claims)
Secure authentication and authorization
HIPAA, GDPR, PCI DSS compliance
Response time <2 seconds for 95% of queries
99.9% uptime SLA
Business Requirements:
Reduce customer service operational costs
Improve customer satisfaction and loyalty
Maintain Seven Corners brand voice and values
Support business growth without proportional headcount increase
Provide competitive advantage in travel insurance market
Out of Scope
Phase 1 Exclusions (may be added in later phases):
Automated claim approvals or denials (requires human review)
Policy underwriting decisions (regulatory/compliance constraints)
Payment disputes or billing adjustments (requires human judgment)
Medical advice or diagnosis (liability concerns)
Real-time language translation during human agent calls (separate project)
Integration with partner travel agencies or OTAs (future consideration)
White-label solutions for resellers (not in current roadmap)
Permanent Exclusions:
Replace human customer service agents entirely (augmentation, not replacement)
Provide medical advice or emergency medical services (outside scope of insurance company)
Make underwriting or actuarial decisions (regulatory requirements)
Guarantee claim approval or coverage (requires policy review and adjudication)
Acceptance Criteria
Virtual Assistant Quality:
90%+ accuracy in intent classification for top 30 inquiries
85%+ customer satisfaction rating for automated interactions
<5% conversation abandonment rate
95% of responses are factually accurate and policy-compliant
Zero instances of providing incorrect coverage information
Technical Performance:
Average response latency <2 seconds
99.9% uptime excluding planned maintenance
Successful integration with policy/CRM systems (API response time <500ms)
Support concurrent usage by 500+ customers without degradation
All security and compliance requirements met (HIPAA, GDPR, PCI DSS)
Business Outcomes:
40% containment rate achieved within 6 months
25% CSAT improvement within 12 months
50% response time reduction within 12 months
Positive ROI within 24 months
Customer service cost per interaction reduced by 35%
Assumptions
Resource Assumptions:
Dedicated project team will be available throughout project duration.
  Impact if false: Timeline extends by 2-4 months, scope reduction required
  Likelihood: High
  Owner: Project Sponsor
  Validation: Resource commitment confirmed in project charter
Microsoft 365 and Azure subscriptions are already in place or will be procured.
  Impact if false: 4-6 week delay for procurement, potential budget impact
  Likelihood: High
  Owner: IT Director
  Validation: Licensing review completed by Month 1
Customer service subject matter experts available 10 hours/week for conversation design.
  Impact if false: Conversation quality suffers, longer design iterations
  Likelihood: Medium-High
  Owner: Customer Service Director
  Validation: Time allocation confirmed with managers
Technical Assumptions:
Policy administration and CRM systems have accessible APIs or can be developed.
  Impact if false: Significant delay (3-6 months), potential scope reduction, custom integration work
  Likelihood: Medium
  Owner: IT Architect
  Validation: API documentation review and technical feasibility assessment in Month 1
Existing customer service knowledge base and FAQs are documented and accurate.
  Impact if false: 2-4 weeks additional time for content creation, potential quality issues
  Likelihood: Medium
  Owner: Customer Service Manager
  Validation: Content audit completed in Week 2
Azure AI services can handle expected concurrent user load (500+ simultaneous conversations).
  Impact if false: Additional infrastructure costs, performance optimization required
  Likelihood: High
  Owner: Cloud Architect
  Validation: Load testing during POC phase
Third-party travel advisory APIs (CDC, State Department) remain available and free/low-cost.
  Impact if false: Remove travel advisory feature or find alternative data sources
  Likelihood: High
  Owner: Product Manager
  Validation: API terms of service review, backup sources identified
Stakeholder Assumptions:
Executive sponsor will provide air cover and remove organizational obstacles.
  Impact if false: Project delays due to competing priorities, resource contention
  Likelihood: High
  Owner: Executive Sponsor
  Validation: Written commitment in project charter
Customer service team will embrace AI as augmentation, not replacement.
  Impact if false: Change resistance, poor adoption, agent attrition
  Likelihood: Medium
  Owner: Change Manager
  Validation: Early stakeholder engagement, transparent communication
Customers will accept and use virtual assistant for routine inquiries.
  Impact if false: Low adoption, continued preference for human agents, ROI not achieved
  Likelihood: High
  Owner: Product Manager
  Validation: Pilot testing with 100+ customers, user feedback sessions
Business Assumptions:
Budget of $350,000-$500,000 will remain committed throughout 18-month project.
  Impact if false: Scope reduction, timeline extension, or project cancellation
  Likelihood: High
  Owner: CFO / Project Sponsor
  Validation: Quarterly budget reviews, financial commitment letter
No major organizational restructuring or M&A activity during project timeline.
  Impact if false: Changing priorities, team disruption, potential project cancellation
  Likelihood: Medium-High
  Owner: Executive Sponsor
  Validation: Regular executive updates, contingency planning
Travel insurance market and customer expectations remain relatively stable.
  Impact if false: Requirement changes, competitive pressure, feature additions
  Likelihood: Medium
  Owner: Chief Marketing Officer
  Validation: Quarterly market analysis, competitive monitoring
Regulatory/Compliance Assumptions:
Current insurance regulations permit AI-assisted customer service without material changes.
  Impact if false: Compliance delays, feature restrictions, disclosure requirements
  Likelihood: High
  Owner: Legal / Compliance Officer
  Validation: Regulatory review in Month 1, ongoing monitoring
HIPAA, GDPR, and PCI DSS compliance can be achieved with Microsoft's standard offerings.
  Impact if false: Additional security controls required, increased costs, timeline delay
  Likelihood: High
  Owner: Information Security Officer
  Validation: Security assessment during architecture design phase
Constraints
Time Constraints:
Phase 1 MVP must launch within 4 months to meet business goals
Full deployment (Phase 2) must complete within 12 months
Project must show measurable ROI within 24 months
Budget Constraints:
Total project budget capped at $500,000 (including all phases)
Phase 1 budget limited to $150,000
Ongoing operational costs must not exceed $5,000/month
Resource Constraints:
Maximum 2 full-time equivalent developers available
Limited availability of customer service SMEs (10 hours/week)
No dedicated data science team (rely on Azure AI Foundry managed services)
Technical Constraints:
Must integrate with existing legacy policy administration system (limited API capabilities)
Cannot modify core business systems (policy admin, claims) - read-only access only in Phase 1
Must use Microsoft technology stack due to existing enterprise agreement
Must comply with company security and networking policies (VPN, firewall rules)
Regulatory Constraints:
HIPAA compliance required for medical travel insurance information
GDPR compliance for European travelers
PCI DSS compliance for payment processing
State insurance regulations on automated customer service disclosures
Cannot make binding coverage determinations without human review
Business Constraints:
Must maintain Seven Corners brand voice and customer service standards
Cannot reduce customer service headcount during implementation (augmentation only)
Must support existing SLA for customer response times during transition
Requires customer consent for AI interaction (opt-out to human agent always available)
Major Milestones
Month 1: Discovery & Planning
Week 2: Kickoff meeting and stakeholder alignment
Week 3: Technical architecture approved
Week 4: Detailed project plan and timeline finalized
Month 2: POC Development
Week 6: Copilot Studio POC environment configured
Week 7: FAQ bot prototype with top 5 inquiries
Week 8: POC user testing with internal team
Month 3: MVP Development
Week 10: Azure AI Search knowledge base deployed
Week 11: Policy lookup integration (read-only) complete
Week 12: MVP testing with 50-100 pilot customers
Month 4: Phase 1 Launch
Week 14: Customer service team training completed
Week 15: Production deployment to website chat
Week 16: Phase 1 success metrics validated (Milestone: MVP Launch)
Month 6: Phase 1 Optimization
Month 6 checkpoint: 30% containment rate achieved
Conversation optimization based on 2 months usage data
Expansion planning approved
Month 9: Phase 2 Complete
Multi-channel deployment (mobile, WhatsApp, Teams)
Top 30 inquiries automated
40% containment rate achieved (Milestone: Phase 2 Launch)
Month 12: Business Case Validation
25% CSAT improvement demonstrated
50% response time reduction confirmed
ROI projection validated (Milestone: Business Goals Achieved)
Month 18: Phase 3 Complete
Azure AI Foundry custom models deployed
Voice channel operational
Multi-agent system live (Milestone: Advanced AI Deployment)

## Slide 6: Approach
Methodology and Framework
This project will use a Hybrid Agile approach combining Agile development practices with structured governance for an 18-month timeline. The hybrid methodology balances the need for rapid iteration and stakeholder feedback (Agile) with the requirements for enterprise architecture review, compliance validation, and financial governance (Waterfall gates).
Agile Elements:
Two-week sprints for development work
Daily standups for core team coordination
Sprint reviews with product owner and stakeholders
Retrospectives for continuous improvement
Iterative delivery of functional increments
Waterfall Gates:
Phase gate reviews at major milestones (POC, MVP, Phase 2, Phase 3)
Architecture review board approval for integrations
Security and compliance sign-offs before production deployment
Budget approval process for phase transitions
Formal UAT and stakeholder acceptance
Execution Strategy
Phase 1: Foundation (Months 1-4)
Month 1: Discovery & Technical Setup
Week 1-2: Stakeholder workshops to define top customer inquiries, conversation flows, success metrics
Week 2-3: Technical discovery (system APIs, data sources, integration points)
Week 3-4: Architecture design and approval, team onboarding, tool provisioning
Month 2: Proof of Concept
Sprint 1-2: Build FAQ bot with top 5 inquiries in Copilot Studio
Sprint 3-4: Integrate Azure AI Search with sample knowledge base, basic policy lookup
Internal testing and stakeholder demos
POC evaluation: Go/No-Go decision for MVP
Month 3: MVP Development
Sprint 5-6: Expand to top 10 inquiries, conversation flow refinement
Sprint 7-8: Production integrations (policy API, authentication, analytics)
Sprint 9: Hardening (error handling, edge cases, performance tuning)
UAT with customer service team
Month 4: Launch & Stabilization
Sprint 10: Pilot deployment to 100 customers, monitor closely
Sprint 11: Customer service team training, rollout plan execution
Sprint 12: Full production launch to website chat, immediate support and monitoring
Sprint reviews after 2 weeks, 1 month, 2 months
Phase 2: Expansion (Months 5-9)
Sprints 13-18: Multi-channel rollout (mobile, WhatsApp, Teams)
Sprints 19-22: Expand automation to top 30 inquiries
Sprints 23-24: Enhanced integrations (claims, CRM, payments)
Continuous optimization based on analytics and customer feedback
Phase 3: Advanced AI (Months 10-18)
Sprints 25-30: Azure AI Foundry custom model development (policy recommendations, sentiment analysis)
Sprints 31-34: Voice channel development and integration
Sprints 35-36: Multi-agent system design and deployment
Performance tuning, final optimizations
Key Processes
Decision-Making:
Tactical decisions (conversation wording, UI tweaks): Product Owner authority
Technical decisions (architecture, tooling): Technical Lead with Architecture Review Board input
Scope/budget decisions (new features, phase changes): Steering Committee (monthly meetings)
Strategic decisions (cancellation, major pivots): Executive Sponsor with CFO approval
Communication and Reporting:
Daily: Core team standup (15 minutes)
Bi-weekly: Sprint review with Product Owner and key stakeholders
Monthly: Steering Committee update (metrics, budget, risks)
Quarterly: Executive business review (ROI, strategic alignment)
Ad-hoc: Slack channel for team collaboration, email for formal communications
Quality Assurance:
Conversation quality: SME review of all responses before production
Technical quality: Automated testing (unit tests, integration tests), code reviews
User acceptance: UAT with customer service team before each release
Production quality: Real-time monitoring, customer feedback collection, A/B testing
Compliance quality: Security reviews, privacy assessments, regulatory audits
Risk Management:
Risk identification: Weekly team discussions, monthly stakeholder input
Risk assessment: Likelihood and impact scoring, prioritization
Risk mitigation: Proactive plans for high-priority risks
Risk monitoring: Dashboard tracking, regular reviews at Steering Committee
Issue escalation: RAID log (Risks, Assumptions, Issues, Dependencies), escalation to Sponsor for blockers
Change Management:
Change requests: Documented via project management tool, impact analysis required
Approval process: Product Owner for minor, Steering Committee for major
Impact assessment: Scope, schedule, budget, risk implications
Communication: All stakeholders notified of approved changes
Version control: All configuration and code changes tracked in Git
Resource Strategy
Team Structure: Matrix Organization
Core team members report to functional managers but are dedicated to project for defined percentage of time.
Core Project Team:
Project Manager (1 FTE) - Dedicated full-time
  Overall project coordination, timeline management, stakeholder communication
  Risk and issue management, budget tracking
  Reports to: IT PMO Director
Product Owner (0.5 FTE) - 50% time allocation
  Conversation design, feature prioritization, acceptance criteria
  Stakeholder liaison, UAT coordination
  Reports to: VP of Customer Experience
Technical Lead / Cloud Architect (0.75 FTE) - 75% time
  Architecture design, platform selection, integration strategy
  Code reviews, technical governance
  Reports to: Director of IT Architecture
Developers (2 FTE) - Two full-time developers
  Copilot Studio conversation development
  Azure AI Search configuration and optimization
  API integrations and custom connectors
  Reports to: Engineering Manager
Business Analyst (0.5 FTE) - 50% time
  Requirements gathering, process documentation
  Test case creation, UAT facilitation
  Reports to: Business Analysis Manager
QA/Test Engineer (0.5 FTE) - 50% time ramping to 1 FTE during UAT
  Test plan creation, automated test development
  Regression testing, performance testing
  Reports to: QA Manager
Subject Matter Experts (Part-Time):
Customer Service SMEs (3 people @ 10 hours/week each)
  Conversation review, FAQ accuracy validation
  UAT participation, training material review
  Reports to: Customer Service Director
Information Security Officer (0.25 FTE) - 25% time
  Security architecture review, compliance validation
  Penetration testing coordination, audit support
  Reports to: CISO
Legal/Compliance (0.1 FTE) - As-needed consultation
  Regulatory review, disclosure requirements
  Privacy policy updates, customer consent
  Reports to: General Counsel
External Resources:
Microsoft Partner (if needed) - Budget: $50,000
  Accelerate Copilot Studio development with expertise
  Azure AI Foundry best practices and optimization
  Knowledge transfer to internal team
Conversation Design Consultant (Phase 1 only) - Budget: $20,000
  Best practices for conversational UX
  Multi-turn conversation patterns
  Empathy and tone guidelines for insurance context
Tools and Technology:
Development:
Microsoft Copilot Studio (conversational AI platform)
Azure AI Foundry (custom AI models - Phase 3)
Azure AI Search (knowledge base and document retrieval)
Azure DevOps (version control, CI/CD, work tracking)
Power Platform (integrations, connectors)
Project Management:
Azure DevOps Boards (backlog, sprint planning)
Microsoft Teams (collaboration and communication)
Microsoft Project or Smartsheet (Gantt charts, timeline)
Power BI (dashboards and reporting)
Testing:
Playwright or Selenium (automated testing)
Azure Load Testing (performance validation)
User testing platform (UserTesting.com or similar)
Monitoring:
Azure Application Insights (performance, errors)
Power BI (conversation analytics, KPI dashboards)
Customer feedback tools (surveys, CSAT)
Stakeholder Engagement
Primary Stakeholders:
Executive Sponsor (CEO or COO)
Engagement: Monthly steering committee, quarterly business reviews
Role: Strategic direction, obstacle removal, budget approval
Communication: Executive summaries, ROI updates
VP of Customer Experience (Product Owner)
Engagement: Bi-weekly sprint reviews, daily availability for questions
Role: Feature prioritization, acceptance criteria, customer advocacy
Communication: Sprint demos, feature documentation
Customer Service Director
Engagement: Weekly check-ins, monthly team meetings
Role: Agent engagement, training coordination, change management
Communication: Team newsletters, training sessions, feedback sessions
IT Director
Engagement: Bi-weekly technical sync, architecture reviews
Role: Infrastructure support, security compliance, integration approvals
Communication: Technical documentation, architecture diagrams
CFO
Engagement: Quarterly financial reviews, phase gate approvals
Role: Budget oversight, ROI validation, financial governance
Communication: Financial reports, budget variance analysis
Secondary Stakeholders:
Customer Service Agents (End Users)
Engagement: UAT participation, feedback sessions, training
Role: Provide input on conversation quality, identify gaps, advocate for customer needs
Communication: Workshops, demos, feedback surveys
Customers (End Users)
Engagement: Pilot testing, surveys, usage analytics
Role: Use the virtual assistant, provide feedback, validate value
Communication: In-app messaging, email updates, satisfaction surveys
Marketing Team
Engagement: Monthly updates, launch planning sessions
Role: Customer communication, brand alignment, feature promotion
Communication: Marketing briefs, launch materials
Legal/Compliance
Engagement: Phase gate reviews, regulatory checkpoints
Role: Ensure compliance, review disclosures, approve policies
Communication: Compliance reports, audit findings
Collaboration and Feedback Mechanisms:
Workshops: Monthly conversation design sessions with SMEs
Demos: Bi-weekly sprint reviews with working software
Surveys: Post-interaction customer satisfaction, quarterly stakeholder pulse checks
Office Hours: Weekly open sessions for stakeholders to ask questions
Feedback Portal: Centralized location for suggestions and issues
Approval Processes:
Sprint acceptance: Product Owner approves each sprint deliverable
Phase gates: Steering Committee approves phase transitions (POC→MVP→Phase 2→Phase 3)
Production releases: Technical Lead + Information Security Officer + Product Owner sign-off
Budget changes: CFO approval for >$10K variances
Scope changes: Steering Committee for major, Product Owner for minor

## Slide 7: Deliverables
Phase 1 Deliverables (Months 1-4)
1. Copilot Studio Virtual Assistant (External Deliverable)
Functional conversational AI on Seven Corners website
Automates top 10 customer inquiries
Bilingual support (English, Spanish minimum)
Human escalation with full transcript
Acceptance Criteria: 90% intent accuracy, <2s response time, 85% CSAT from pilot users
2. Azure AI Search Knowledge Base (Internal Deliverable)
Indexed content: 50+ FAQ entries, 20+ policy documents, coverage summaries
Semantic search tuned for travel insurance terminology
Search relevance >80% for test query set
Acceptance Criteria: Retrieves correct answer in top 3 results for 95% of test queries
3. Policy Lookup Integration (Internal Deliverable)
Read-only API connection to policy administration system
Customer authentication and authorization
Policy details retrieval by policy number
Acceptance Criteria: <500ms response time, 99.9% uptime, secure data transmission
4. Analytics Dashboard (Internal Deliverable)
Conversation metrics (volume, containment rate, escalation reasons)
Customer satisfaction tracking
System performance monitoring
Acceptance Criteria: Real-time data refresh, exportable reports, accessible to stakeholders
5. Training Materials (External Deliverable)
Customer service team training curriculum (4-hour program)
Administrator guide for bot maintenance
Troubleshooting playbook
Acceptance Criteria: 90% of agents rate training as "effective" or "very effective"
6. Project Documentation (Internal Deliverable)
Architecture design document
API integration specifications
Conversation flow diagrams
Acceptance Criteria: Complete, accurate, approved by technical review board
7. Customer Communication Materials (External Deliverable)
Website announcement of new AI assistant
FAQ about virtual assistant usage
Privacy policy updates (AI data handling)
Acceptance Criteria: Legal/compliance approval, brand alignment, customer clarity
Phase 2 Deliverables (Months 5-9)
8. Multi-Channel Deployment (External Deliverable)
Mobile app integration (iOS and Android)
WhatsApp Business channel
Microsoft Teams channel (internal/partner use)
Facebook Messenger support
Acceptance Criteria: Consistent experience across channels, <3s response time per channel
9. Expanded Automation (External Deliverable)
Top 30 customer inquiries automated (up from 10)
Claims status tracking capability
Travel advisory integration (CDC, State Department)
Proactive notifications (policy renewal, claim updates)
Acceptance Criteria: 40% containment rate, 90% intent accuracy maintained
10. Enhanced Integrations (Internal Deliverable)
CRM integration (customer history, preferences)
Service request creation in policy system
Payment gateway integration (quotes, premium collection)
Acceptance Criteria: End-to-end workflows functional, data sync accuracy >99%
11. Optimization Report (Internal Deliverable)
Analysis of 6 months usage data
Conversation flow improvements implemented
Performance optimization results
Acceptance Criteria: Measurable improvement in containment rate, CSAT, response time
Phase 3 Deliverables (Months 10-18)
12. Custom AI Models (Internal Deliverable)
Policy recommendation engine (Azure AI Foundry)
Sentiment analysis for escalation prioritization
Intent classification model trained on Seven Corners data
Acceptance Criteria: >85% accuracy, integrated with Copilot Studio, improves customer outcomes
13. Voice Channel (External Deliverable)
Phone-based virtual assistant using Azure Voice Live API
Speech-to-text optimized for insurance terminology
Integration with call center platform
Acceptance Criteria: >90% transcription accuracy, seamless human handoff, 75% CSAT
14. Multi-Agent System (Internal Deliverable)
Specialist agents (policies, claims, billing, travel assistance)
Coordinated handoffs between agents
Unified conversation context
Acceptance Criteria: Customers unaware of multi-agent architecture, improved resolution rates
15. Final Business Case Validation (Internal Deliverable)
ROI analysis with 18 months actual data
Business metrics achievement report (CSAT, response time, cost reduction)
Lessons learned and future roadmap
Acceptance Criteria: Positive ROI demonstrated, business goals achieved, executive approval for ongoing investment
Ongoing Deliverables (Throughout Project)
16. Sprint Deliverables (Internal)
Working software increments every 2 weeks
Sprint reports and demos
Updated backlog and roadmap
17. Monthly Steering Committee Reports (Internal)
Progress against timeline and budget
Key metrics and KPIs
Risks and issues dashboard
Upcoming decisions and approvals needed
18. Quarterly Business Reviews (Internal)
Executive summary of accomplishments
Financial performance (budget vs. actual, ROI tracking)
Strategic alignment and value realization
Recommendations for next quarter

## Slide 8: Project Team
Core Team Roles and Responsibilities
Project Manager - Sarah Johnson (Placeholder Name)
Time Allocation: 100% (Full-time dedicated)
Key Responsibilities:
  Overall project coordination and timeline management
  Stakeholder communication and expectation management
  Risk and issue identification, tracking, and mitigation
  Budget monitoring and variance reporting
  Facilitate steering committee meetings and decision-making
  Remove blockers and escalate to sponsor when needed
Success Criteria: On-time, on-budget delivery with stakeholder satisfaction
Product Owner - Michael Chen (Customer Experience)
Time Allocation: 50% (20 hours/week)
Key Responsibilities:
  Define conversation flows and user experience
  Prioritize features in product backlog
  Define acceptance criteria for deliverables
  Conduct sprint reviews and provide feedback
  Liaison between business stakeholders and technical team
  Make trade-off decisions (scope vs. time vs. quality)
Success Criteria: High-quality conversational experience, business goals achieved
Technical Lead / Cloud Architect - Priya Patel (IT Architecture)
Time Allocation: 75% (30 hours/week)
Key Responsibilities:
  Design solution architecture (Copilot Studio, Azure AI, integrations)
  Technology selection and platform configuration
  Code reviews and technical quality assurance
  Integration strategy and API design
  Performance optimization and scalability planning
  Security architecture and compliance validation
Success Criteria: Robust, scalable, secure technical solution
Senior Developer - Alex Martinez (Engineering)
Time Allocation: 100% (Full-time dedicated)
Key Responsibilities:
  Copilot Studio conversation development and testing
  Azure AI Search configuration and optimization
  Custom connector development for backend systems
  API integrations (policy, CRM, claims, payment)
  Automated testing and CI/CD pipeline
  Technical documentation
Success Criteria: High-quality code, timely feature delivery
Developer - Jordan Lee (Engineering)
Time Allocation: 100% (Full-time dedicated)
Key Responsibilities:
  Copilot Studio conversation development
  Knowledge base content management and search tuning
  Multi-channel deployment (mobile, WhatsApp, Teams)
  Bug fixes and production support
  Performance monitoring and optimization
  Collaboration with Senior Developer on complex integrations
Success Criteria: Reliable, performant features across all channels
Business Analyst - Emily Rodriguez (Business Analysis)
Time Allocation: 50% (20 hours/week)
Key Responsibilities:
  Gather and document business requirements
  Process mapping and workflow documentation
  Create test cases and UAT scripts
  Facilitate UAT sessions with customer service team
  Gap analysis and recommendations
  Training material creation and review
Success Criteria: Clear requirements, successful UAT, smooth adoption
QA/Test Engineer - David Kim (Quality Assurance)
Time Allocation: 50% ramping to 100% during UAT phases
Key Responsibilities:
  Create comprehensive test plans and test cases
  Automated testing framework development
  Regression testing for each release
  Performance and load testing
  Bug tracking and verification
  Quality metrics reporting
Success Criteria: <5% defect escape rate, high test coverage
Subject Matter Experts (Part-Time Contributors)
Customer Service SMEs (3 people)
Time Allocation: 10 hours/week each
Key Responsibilities:
  Review and validate conversation flows for accuracy
  Provide domain expertise on policies, claims, customer pain points
  Participate in UAT and provide feedback
  Review training materials
  Champion AI adoption within customer service team
Success Criteria: Accurate, empathetic conversations that reflect Seven Corners expertise
Information Security Officer - Marcus Thompson
Time Allocation: 25% (10 hours/week)
Key Responsibilities:
  Security architecture review and approval
  Compliance validation (HIPAA, GDPR, PCI DSS)
  Penetration testing coordination
  Incident response planning
  Security monitoring and audit support
Success Criteria: Secure solution with zero breaches, all compliance requirements met
Legal/Compliance - Jennifer Adams
Time Allocation: As-needed (estimate 5 hours/month)
Key Responsibilities:
  Regulatory requirements review
  Customer disclosure and consent language approval
  Privacy policy updates
  Audit support for insurance regulators
Success Criteria: Full regulatory compliance, risk mitigation
External Partners
Microsoft Partner (Optional, Budget: $50,000)
Engagement: Phase 1-2, tapering off in Phase 3
Key Responsibilities:
  Copilot Studio and Azure AI Foundry best practices
  Accelerate development with proven patterns
  Technical workshops and knowledge transfer
  Troubleshooting and optimization support
Success Criteria: Faster time-to-value, internal team capability building
Conversation Design Consultant (Phase 1, Budget: $20,000)
Engagement: Months 1-3
Key Responsibilities:
  Conversational UX best practices for insurance domain
  Multi-turn conversation design patterns
  Empathy and tone guidelines
  Review and provide feedback on conversation flows
Success Criteria: High-quality, natural conversations that delight customers
Governance Structure
Steering Committee (Monthly Meetings)
Executive Sponsor (Chair)
VP of Customer Experience
IT Director
CFO
Customer Service Director
Project Manager (reports to committee)
Technical Review Board (Bi-weekly as needed)
Chief Architect
Information Security Officer
IT Director
Technical Lead (presents to board)
Change Advisory Board (Weekly)
Product Owner (Chair)
Technical Lead
Project Manager
Business Analyst
Team Success Factors
Clear roles and responsibilities: RACI matrix created and shared
Strong communication: Daily standups, bi-weekly demos, monthly steering committee
Shared goals: Team rallies around customer satisfaction and operational efficiency metrics
Mutual accountability: Sprint commitments, peer code reviews, collective problem-solving
Trust and respect: Psychological safety, diverse perspectives valued
Right mix of skills: Business + technical + domain expertise
Empowerment: Team has authority to make tactical decisions
Leadership support: Executive sponsor actively engaged and removing barriers

## Slide 9: Timeline
High-Level Project Timeline (18 Months)
Total Duration: 18 months (78 weeks) Project Start: Month 1, Week 1 Project Completion: Month 18, Week 78 Critical Path: Discovery → POC → MVP → Multi-Channel → Voice Integration
Phase Breakdown
Phase 1: Foundation (Months 1-4, Weeks 1-16)
Month 1: Discovery & Planning
Week 1: Project kickoff, stakeholder workshops (Milestone: Project Kick-off)
Week 2: Requirements gathering, technical discovery
Week 3: Architecture design, tool provisioning
Week 4: Detailed project plan approval (Milestone: Plan Approval)
Month 2: Proof of Concept
Weeks 5-6: Copilot Studio POC environment, top 5 FAQ automation
Weeks 7-8: Azure AI Search integration, policy lookup prototype
Week 8 end: POC demo and Go/No-Go decision (Milestone: POC Complete)
Month 3: MVP Development
Weeks 9-10: Expand to top 10 inquiries, conversation refinement
Weeks 11-12: Production integrations (policy API, auth, analytics)
Week 12 end: MVP ready for UAT (Milestone: MVP Development Complete)
Month 4: Launch & Stabilization
Week 13: Pilot with 100 customers, monitoring
Week 14: Customer service team training
Week 15: Production launch to website chat (Milestone: Phase 1 Launch)
Week 16: Post-launch support and optimization
Phase 2: Expansion (Months 5-9, Weeks 17-36)
Months 5-6: Multi-Channel Deployment
Weeks 17-20: Mobile app integration (iOS and Android)
Weeks 21-24: WhatsApp Business and Microsoft Teams channels
Week 24 end: Multi-channel live (Milestone: Multi-Channel Deployment)
Months 7-8: Enhanced Capabilities
Weeks 25-28: Expand to top 30 inquiries, claims status tracking
Weeks 29-32: Travel advisory integration, proactive notifications
Week 32 end: Enhanced capabilities live
Month 9: Advanced Integrations & Optimization
Weeks 33-34: CRM integration, service request creation
Weeks 35-36: Payment gateway integration, Phase 2 optimization
Week 36 end: 40% containment rate achieved (Milestone: Phase 2 Complete)
Phase 3: Advanced AI (Months 10-18, Weeks 37-78)
Months 10-12: Custom AI Models
Weeks 37-42: Azure AI Foundry setup, model development environment
Weeks 43-48: Policy recommendation engine, sentiment analysis, intent classification
Week 48 end: Custom models deployed (Milestone: Custom AI Live)
Months 13-15: Voice Channel
Weeks 49-54: Voice Live API integration, speech-to-text optimization
Weeks 55-60: Call center platform integration, testing
Week 60 end: Voice channel operational (Milestone: Voice Channel Launch)
Months 16-18: Multi-Agent System & Finalization
Weeks 61-66: Multi-agent architecture design and development
Weeks 67-72: Specialist agents deployment, coordinated handoffs
Weeks 73-76: System-wide optimization, performance tuning
Weeks 77-78: Final business case validation, project closeout
Week 78: Project completion (Milestone: Project Complete)
Key Milestones Summary
Milestone | Week | Description
Project Kick-off | 1 | Stakeholder alignment, team formation
Plan Approval | 4 | Detailed project plan and budget approved
POC Complete | 8 | Proof of concept demonstrates feasibility
MVP Development Complete | 12 | MVP ready for user acceptance testing
Phase 1 Launch | 15 | Production launch to website chat
Multi-Channel Deployment | 24 | Mobile, WhatsApp, Teams channels live
Phase 2 Complete | 36 | 40% containment rate achieved
Custom AI Live | 48 | Azure AI Foundry models operational
Voice Channel Launch | 60 | Phone-based virtual assistant deployed
Project Complete | 78 | All phases complete, ROI validated

## Slide 10
Dependencies and Critical Path
Critical Path Tasks:
Architecture approval → POC development → MVP development → Production launch
API access to policy/CRM systems (blocker if not available by Month 2)
Microsoft platform licensing and provisioning (must complete by Week 2)
Customer service SME availability (conversation quality depends on their input)
Security and compliance approvals (gates before production deployments)
External Dependencies:
Policy administration system API availability (Owner: IT Director)
Microsoft 365 and Azure licensing procurement (Owner: IT Procurement)
Customer service team availability for UAT (Owner: CS Director)
Third-party travel advisory API access (Owner: Product Manager)
Timeline Risk Mitigation
Buffer Time:
10% buffer built into each phase for unforeseen issues
2-week contingency reserve before major milestones
Quarterly timeline reviews with option to adjust later phases
Parallel Work:
Documentation and training materials developed in parallel with technical work
Multi-channel development can occur concurrently (mobile, WhatsApp, Teams)
Azure AI Foundry exploration begins during Phase 2 to de-risk Phase 3
Fast-Track Options (if needed):
Engage Microsoft partner to accelerate development
Reduce scope (e.g., defer voice channel to post-project)
Extend Phase 1 timeline, compress later phases based on learnings

## Slide 11: Investment
Total Project Budget: $450,000
Budget by Phase:
Phase 1 (Foundation): $150,000
Phase 2 (Expansion): $175,000
Phase 3 (Advanced AI): $125,000
Detailed Cost Breakdown
Personnel Costs: $275,000 (61%)
Internal Team (Fully Burdened Rates):
Project Manager (18 months @ $12,000/month): $216,000
Product Owner (50% allocation, 18 months @ $6,000/month): $108,000
Technical Lead (75% allocation, 18 months @ $9,000/month): $162,000
Senior Developer (18 months @ $10,000/month): $180,000
Developer (18 months @ $8,500/month): $153,000
Business Analyst (50% allocation, 18 months @ $5,000/month): $90,000
QA Engineer (50% avg, 18 months @ $4,500/month): $81,000
Subtotal Internal Labor: $990,000
Note: Internal labor is allocated from existing headcount and represents opportunity cost rather than incremental cash outlay. For budget purposes, we are accounting for 2 FTE incremental contractors if internal resources are not available at $275,000 (Developer positions outsourced).
External Resources:
Microsoft Partner consultation: $50,000
Conversation Design Consultant: $20,000
Subtotal External Labor: $70,000
Total Personnel: $345,000 (assuming 2 developer contractors + external consultants)
Technology Costs: $85,000 (19%)
Microsoft Platform Licensing (18 months):
Copilot Studio licenses and usage: $24,000 ($1,333/month × 18)
Azure AI Search (standard tier): $18,000 ($1,000/month × 18)
Azure AI Foundry (Phase 3, 9 months): $27,000 ($3,000/month × 9)
Azure infrastructure (compute, storage, networking): $12,000 ($667/month × 18)
Power Platform premium connectors: $4,000
Integration and Development Tools:
Azure DevOps (included in enterprise agreement): $0
Testing tools (Playwright, load testing): $2,000
Subtotal Technology: $87,000
External Services: $70,000 (16%)
Microsoft Partner (Copilot Studio expertise): $50,000
Conversation Design Consultant: $20,000
Subtotal External Services: $70,000
Training and Change Management: $15,000 (3%)
Customer service team training (materials, facilitator, time): $8,000
Executive workshops and stakeholder communication: $3,000
End-user documentation and support materials: $2,000
Change management activities (surveys, feedback sessions): $2,000
Subtotal Training: $15,000
Other Costs: $10,000 (2%)
Travel (if needed for vendor meetings, conferences): $3,000
Compliance and security audits (penetration testing): $5,000
Miscellaneous (contingency for small purchases): $2,000
Subtotal Other: $10,000
Contingency Reserve (10%): $45,000
Buffer for scope changes, unforeseen technical challenges, market rate changes
Total Project Investment: $450,000
Cost-Benefit Analysis
Expected Benefits (Annual, Steady State after Year 2):
Cost Savings:
Customer service operational costs (40% containment × $15 avg cost per interaction × 100,000 annual interactions): $600,000/year
Agent productivity gains (30% faster handle time): $150,000/year
Reduced call center overtime and peak staffing: $50,000/year
Total Annual Cost Savings: $800,000
Revenue Impact:
Improved customer satisfaction leading to higher retention: $100,000/year (conservative estimate)
Competitive differentiation enabling premium pricing: $50,000/year
Total Annual Revenue Impact: $150,000
Total Annual Benefit: $950,000
ROI Calculation:
Project Investment: $450,000
Year 1 Benefits: $300,000 (partial year, ramp-up)
Year 2 Benefits: $800,000 (steady state cost savings + revenue)
Year 3 Benefits: $950,000 (full benefit realization)
3-Year Total Benefits: $2,050,000
3-Year Net Benefits: $2,050,000 - $450,000 = $1,600,000
ROI: ($1,600,000 / $450,000) × 100% = 356% over 3 years
Payback Period: ~9 months (Month 13 of project, Month 4 after full launch)
Ongoing Operational Costs (Annual):
Microsoft platform licensing: $48,000/year
System maintenance and updates: $24,000/year (0.5 FTE developer)
Conversation content updates and optimization: $12,000/year (SME time)
Total Ongoing Costs: $84,000/year
Net Annual Benefit (after ongoing costs): $950,000 - $84,000 = $866,000/year
Funding Source
Internal IT budget allocation: $300,000
Customer Experience budget contribution: $100,000
Digital transformation fund: $50,000
Total Committed Funding: $450,000
Payment Schedule
Months 1-4 (Phase 1): $150,000
  Month 1: $40,000 (team ramp-up, tool provisioning)
  Month 2-3: $60,000 (POC and MVP development)
  Month 4: $50,000 (launch and stabilization)
Months 5-9 (Phase 2): $175,000
  Months 5-6: $75,000 (multi-channel development)
  Months 7-9: $100,000 (enhanced capabilities and integrations)
Months 10-18 (Phase 3): $125,000
  Months 10-12: $50,000 (Azure AI Foundry setup and models)
  Months 13-15: $45,000 (voice channel development)
  Months 16-18: $30,000 (multi-agent system and closeout)
Budget Assumptions
Internal developer rates based on current market rates for contractors
Microsoft platform costs based on published pricing (subject to enterprise agreement discounts)
Assumes no major change in scope or regulatory requirements
Assumes existing infrastructure (network, security, identity) can support solution without major upgrades
Travel costs assume local team (minimal travel required)
Budget Risk Mitigation
10% contingency reserve ($45,000) for unforeseen expenses
Monthly budget reviews and variance analysis
Formal change request process for scope additions
Quarterly financial reviews with CFO
Value Beyond ROI
Intangible Benefits:
Enhanced brand reputation for innovation and customer service
Improved employee morale (agents focus on meaningful work, not repetitive inquiries)
Competitive advantage in crowded travel insurance market
Foundation for future AI initiatives across Seven Corners
Data and insights about customer needs informing product development
Scalability without proportional headcount growth

## Slide 12: Risk Register (Top 10 Risks)
Risk | Likelihood | Impact | Mitigation Strategy | Owner
Limited API access to legacy policy system | Medium | High | Early technical discovery, budget for custom middleware, consider read-only workarounds | Technical Lead
Low customer adoption of virtual assistant | Medium | High | Extensive pilot testing, clear value proposition, prominent placement, human opt-out always available | Product Owner
Resistance from customer service team | Medium | Medium | Early engagement, transparent communication, emphasize augmentation not replacement, involve in design | Change Manager
Integration complexity exceeds estimates | Medium | High | Proof of concept validates integrations, Microsoft partner engagement, phased approach with fallbacks | Technical Lead
Budget overruns due to scope creep | Medium | Medium | Formal change request process, steering committee governance, protect Phase 1 scope | Project Manager
Microsoft platform pricing changes | Low | Medium | Enterprise agreement provides price lock, monitor Microsoft announcements, ROI cushion | CFO
Security or compliance issues delay launch | Low | High | Early InfoSec engagement, compliance review in architecture phase, penetration testing before launch | InfoSec Officer
Key personnel turnover (developer, PM) | Low | High | Knowledge sharing, documentation, overlapping team members, Microsoft partner as backup | Project Sponsor
Regulatory changes require design modifications | Low | Medium | Monitor regulatory landscape, build flexibility into design, legal counsel in loop | Legal/Compliance
Competitive offerings diminish differentiation | Medium | Low | Focus on Seven Corners-specific value, continuous innovation roadmap beyond Phase 3 | Product Owner

## Slide 13: Success Criteria and KPIs
Phase 1 (Month 4)
✅ Virtual assistant live on website chat
✅ Top 10 inquiries automated with 90%+ intent accuracy
✅ 85%+ CSAT from pilot users
✅ <2 second average response time
✅ 20%+ containment rate
Phase 2 (Month 9)
✅ Multi-channel deployment (mobile, WhatsApp, Teams)
✅ Top 30 inquiries automated
✅ 40%+ containment rate
✅ Integrations with policy, CRM, claims systems operational
Phase 3 (Month 18)
✅ Voice channel operational
✅ Custom AI models deployed (Azure AI Foundry)
✅ Multi-agent system live
✅ 60%+ containment rate
Business Goals (Month 12)
✅ 25% customer satisfaction improvement
✅ 50% response time reduction
✅ 35% cost per interaction reduction
✅ Positive ROI trajectory confirmed

## Slide 14: Appendices
Appendix A: Glossary
Containment Rate: Percentage of customer inquiries fully resolved by virtual assistant without human escalation
CSAT: Customer Satisfaction Score (typically 1-5 rating)
Intent Accuracy: Percentage of customer queries correctly classified by AI to trigger appropriate response
Human Handoff: Process of transferring conversation from virtual assistant to live customer service agent
Multilingual Support: Ability to conduct conversations in multiple languages
Semantic Search: Search technique that understands meaning and context, not just keyword matching
MVP: Minimum Viable Product - simplest version that delivers value
Appendix B: References
Seven Corners Company Overview (2025-10-10)
Research Summary - Microsoft Copilot Studio and Azure AI Foundry for Customer Service (2025-10-10)
Atlantic Health System - SharePoint Search Replacement (lessons learned on Microsoft platform evaluation)
Microsoft Copilot Studio Documentation (learn.microsoft.com)
Azure AI Foundry Documentation (learn.microsoft.com)
Appendix C: Stakeholder Contact List
[To be populated with actual names and contact information]
Appendix D: RACI Matrix
[To be developed - showing Responsible, Accountable, Consulted, Informed for key decisions and deliverables]

## Slide 15
Document Approval:
Role | Name | Signature | Date
Executive Sponsor | [TBD] |  | 
Product Owner | [TBD] |  | 
IT Director | [TBD] |  | 
CFO | [TBD] |  | 
Project Manager | [TBD] |  | 

## Slide 16
Version History:
Version | Date | Author | Changes
0.1 | 2025-10-10 | Project Team | Initial draft
1.0 | TBD | Project Team | Stakeholder review and approval

## Slide 17
Next Steps:
Review and refine this document with core project team
Conduct discovery workshop with Seven Corners stakeholders to validate assumptions
Obtain executive sponsor approval and budget commitment
Finalize project charter and initiate Phase 1
Status: Draft - Ready for Stakeholder Review and Discovery Workshop